## Schedule - 3 week Sprints
Legend:
Analysis
Design
Elaboration
| Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15
Sprint 0
| Sprint 1 | Sprint 1
Sprint 1
|  |  |  | Sprint 2 | Sprint 2
Sprint 1
Sprint 2
[7 empty] | Sprint 3 | Sprint 3
Sprint 2
Sprint 3
[10 empty] | Sprints 4&5 | Sprints 4&5
Sprint 3
Sprint 4
[13 empty] | Sprints 5&6 | Sprints 5&6
Sprint 4

## Sprint 0 - Schedule 2 weeks
Legend:
Weekend/Holiday
Team Remote
Business Team
Development Team
Team
Sprint Start
Sprint End
Sprint 0 Dates | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Introduction | bar: Day 1
Setup
Role Identification | bar: Day 1
Role Definition | bar: Day 1
Identify Individuals for Role | bar: Day 1
Definition of Ready | bar: Day 1
Definition of Done | bar: Day 1
Enablement
Business Process Management | bar: Day 2
Case Management | bar: Day 2
Pega Terminology | bar: Day 2
Direct Capture Objectives | bar: Day 2
DCO Session Schedule | bar: Day 2
DCO Session
Analysis Meetings | bar: Day 1 to Day 5; Day 8 to Day 12
Project Vision | bar: Day 3
Current State Analysis | bar: Day 3
Future State Analysis | bar: Day 4
Future State Prioritization | bar: Day 4
Design Meetings | bar: Day 1 to Day 5; Day 8 to Day 12
Grooming Session | bar: Day 5; Day 8 to Day 12
Design Session | bar: Day 8 to Day 12
Grooming Playback | bar: Day 12
Business Readiness
Elaboration Meetings | bar: Day 1 to Day 5; Day 8 to Day 12
Sprint Planning
Daily Standup
Sprint Playback
Sprint Review
Sprint Retrospective

## Sprint 0 - Schedule 3 weeks
Legend:
Weekend/Holiday
Team Remote
Business Team
Development Team
Team
Sprint Start
Sprint End
Sprint 0 Dates | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7 | Day8 | Day9 | Day10 | Day11 | Day12 | Day13 | Day14 | Day15 | Day16 | Day17 | Day18 | Day19
Introduction | bar: Day1
Setup
Role Identification | bar: Day1
Role Definition | bar: Day1
Identify Individuals for Role | bar: Day1
Definition of Ready | bar: Day1
Definition of Done | bar: Day1
Enablement
Business Process Management | bar: Day2
Case Management | bar: Day2
Pega Terminology | bar: Day2
Direct Capture Objectives | bar: Day2
DCO Session Schedule | bar: Day2
DCO Session
Analysis Meetings | bar: Day1 to Day5; Day8 to Day12; Day15 to Day19
Project Vision | bar: Day3
Current State Analysis | bar: Day3
Future State Analysis | bar: Day4
Future State Prioritization | bar: Day4
Design Meetings | bar: Day1 to Day5; Day8 to Day12; Day15 to Day19
Grooming Session | bar: Day5; Day8 to Day12; Day15 to Day19
Design Session | bar: Day8 to Day12; Day15 to Day19
Grooming Playback | bar: Day12; Day19
Business Readiness
Elaboration Meetings | bar: Day1 to Day5; Day8 to Day12; Day15 to Day19
Sprint Planning
Daily Standup
Sprint Playback
Sprint Review
Sprint Retrospective

## Sprint 0 - Meetings
Meeting | Date | Agenda | Duration/Meeting | Participants
Project Introduction & Setup | TBD | Role Identification Role Definition Identify Individuals for Roles Definition of Ready Definition of Done | 3 Hrs. | Pega Lead Business Architect (1) Pega Lead System Architect (1) Customer Product Owner (1) Customer SMEs (1-3) Customer Project Manager (1) Customer IT Leads (2) Partner Scrum Master (1) Partner Business Architects (2) Partner Lead System Architects (2) Partner UX Architect (1)
Enablement | TBD | Eight Keys to Success Fundamental Concepts Sprint Schedule & Execution | 3 Hrs. | Pega Lead Business Architect (1) Pega Lead System Architect (1) Customer Product Owner (1) Customer SMEs (1-3) Customer Project Manager (1) Customer IT Leads (2) Partner Scrum Master (1) Partner Business Architects (2) Partner Lead System Architects (2) Partner UX Architect (1)
Project Vision | TBD | Identify business problem, impacted end users, and desired outcomes | 1 Hr. | Customer Project Sponsor (1) Customer Product Owner (1) Pega Lead Business Architect (1)
Current State Analysis | TBD | Identify non-value work and pain points in the current state | 3 Hrs. | Pega Lead Business Architect (1) Pega Lead System Architect (1) Customer Product Owner (1) Customer SMEs (1-3) Customer Business Architect (1) Partner Business Architects (2) Partner Lead System Architects (2) Partner UX Architect (1)
Future State Analysis | TBD | Identify desired features for the future state | 3 Hrs. | Pega Lead Business Architect (1) Pega Lead System Architect (1) Customer Product Owner (1) Customer SMEs (1-3) Customer Business Architect (1) Partner Business Architects (2) Partner Lead System Architects (2) Partner UX Architect (1)
Future State Prioritization | TBD | Identify and prioritize a list of desired features | 1.5 Hrs. | Pega Lead Business Architect (1) Customer Product Owner (1) Customer Business Architect (1) Partner Business Architects (2)
Grooming Session | TBD | Devleop user stories for the priortized features | 3.0 Hrs. | Pega Lead Business Architect (1) Pega Lead System Architect (1) Customer Product Owner (1) Customer SMEs (1-3) Customer Business Architect (1) Partner Business Architects (2) Partner Lead System Architects (2) Partner UX Architect (1)
Design | TBD | Develop proposed solutions for the prioritized features | 0.5 Hr. | Pega Lead Business Architect (1) Pega Lead System Architect (1) Partner Business Architects (2) Partner Lead System Architects (2) Partner UX Architect (1)
Grooming Playback | TBD | Review screen mockups and approve as sprint ready user stories | 1.0 Hr. | Pega Lead Business Architect (1) Pega Lead System Architect (1) Customer Product Owner (1) Customer Business Architect (1) Partner Business Architects (2) Partner Lead System Architects (2) Partner UX Architect (1)

## Sprint 1-N - Schedule 3 weeks
Legend:
Weekend/Holiday
Team Remote
Business Team
Development Team
Team
Sprint Start
Sprint End
Sprint 1 Dates | Day -1 | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21
DCO Session
Analysis Meetings
Project Vision | bar: Day -1
Current State Analysis | bar: Day -1
Future State Analysis | bar: Day 0 to Day 1
Future State Prioritization | bar: Day 1
Design Meetings
Grooming Session | bar: Day 2 to Day 3; Day 6 to Day 10; Day 13 to Day 17
Design Session | bar: Day 3; Day 6 to Day 10; Day 13 to Day 17
Business Readiness | bar: Day 8; Day 15
Grooming Playback | bar: Day 9; Day 16
Elaboration Meetings
Sprint Planning | bar: Day 1
Daily Standup | bar: Day 2 to Day 3; Day 6 to Day 10; Day 13 to Day 17; Day 20 to Day 21
Sprint Playback | bar: Day 10; Day 17
Sprint Review | bar: Day 21
Sprint Retrospective | bar: Day 21

## Sprint 1 - N - Meetings
Meeting | Date | Agenda | Duration/Meeting | Participants
Project Vision | TBD | Identify business problem, impacted end users, and desired outcomes | 1.0 Hr. | Customer Project Sponsor (1) Customer Product Owner (1) Pega Lead Business Architect (1)
Current State Analysis | TBD | Identify non-value work and pain points in the current state | 3.0 Hrs. | Pega Lead Business Architect (1) Pega Lead System Architect (1) Customer Product Owner (1) Customer SMEs (1-3) Customer Business Architect (1) Partner Business Architects (2) Partner Lead System Architects (2) Partner UX Architect (1)
Future State Analysis | TBD | Identify desired features for the future state | 3 Hrs. | Pega Lead Business Architect (1) Pega Lead System Architect (1) Customer Product Owner (1) Customer SMEs (1-3) Customer Business Architect (1) Partner Business Architects (2) Partner Lead System Architects (2) Partner UX Architect (1)
Future State Prioritization | TBD | Identify and prioritize a list of desired features | 1.5 Hrs. | Pega Lead Business Architect (1) Customer Product Owner (1) Customer Business Architect (1) Partner Business Architects (2)
Sprint Planning | TBD | Agree to definition of done, sprint goal, and velocity | 6.0 Hrs. | Scrum Master (1) Product Owner (1) Partner System Architects (5) Customer Tester (1) Customer Trainer (1)
Grooming Session | TBD | Devleop user stories for the priortized features | 3.0 Hrs. | Pega Lead Business Architect (1) Pega Lead System Architect (1) Customer Product Owner (1) Customer SMEs (1-3) Customer Business Architect (1) Partner Business Architects (2) Partner Lead System Architects (2) Partner UX Architect (1)
Daily Standup | TBD | Report on completed, in-progress, and blockers to work | 0.5 Hr. | Scrum Master (1) Product Owner (1) Partner System Architects (5) Customer Tester (1) Customer Trainer (1)
Design | TBD | Develop proposed solutions for the prioritized features | 0.5 Hr. | Pega Lead Business Architect (1) Pega Lead System Architect (1) Partner Business Architects (2) Partner Lead System Architects (2) Partner UX Architect (1)
Business Readiness | TBD | Provide visibility to the roadmap so Training may plan and develop course/reference materials | 1.0 Hr. | Pega Lead Business Architect (1) Training Lead (1) Training Document Specialist (1) Organizational Change (1)
Grooming Playback | TBD | Review screen mockups and approve as sprint ready user stories | 1.0 Hr. | Pega Lead Business Architect (1) Pega Lead System Architect (1) Customer Product Owner (1) Customer Business Architect (1) Partner Business Architects (2) Partner Lead System Architects (2) Partner UX Architect (1)
Sprint Playback | TBD | Review and approve built functionality/tasks on a weekly basis | 1.5 Hrs. | Scrum Master (1) Pega Lead Business Architect (1) Pega Lead System Architect (1) Customer Product Owner (1) Customer Tester (1) Customer Trainer (1) Customer SMEs (1-3) Customer Business Architect (1) Partner Business Architects (2) Partner Lead System Architects (2) Partner System Architects (5) Partner UX Architect (1)
Sprint Review | TBD | Review and approve functionality/tasks at end of Sprint | 3.0 Hrs. | Scrum Master (1) Product Owner (1) Partner System Architects (5) Customer Tester (1) Customer Trainer (1)
Sprint Retrospective | TBD | Review processes from the completed Sprint in order for the Team to continuous improve its sprint delivery | 2.0 Hrs. | Scrum Master (1) Product Owner (1) Partner System Architects (5) Customer Tester (1) Customer Trainer (1)